## Traceability Matrix
Traceability Matrix
Prototype Title: | Echoes of the Vault
Scope: | Echoes of the Vault is a single-player, first-person puzzle prototype built in Unreal Engine 5. The player explores an abandoned underground testing vault — learning to move, look, jump, and interact — then solves a timed relay puzzle and a physics-based environmental puzzle before facing the Vault Warden, a boss defeated only by using the mechanics learned earlier in the level. Player health, an MM:SS game timer, a HUD, and win/lose conditions are all required. The prototype runs as one continuous level with no Starter Content or asset packs.
GitHub Repository Link: | https://github.com/kptmail-game/SNHU_GAM303_FPSPuzzle
Class | Functionality | Implementation Description | Program | Begin Phase | Complete Phase | Assigned To | Completed? Y/N | Notes
Player Character | First-Person Camera | Configure the First Person camera component attached to the player pawn. Ensure FOV, head-bob, and look sensitivity are tuned for the puzzle context. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Completed and merged via PR #1 (2026-07-06).
Player Character | WASD Movement | Create Input Action and Input Mapping Context assets for Move (WASD). Implement Enhanced Input in the Player Character Blueprint to drive AddMovementInput. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Completed and merged via PR #1 (2026-07-06).
Player Character | Mouse Look | Create Input Action for Look (mouse X/Y). Wire to AddControllerYawInput and AddControllerPitchInput. Clamp pitch to prevent gimbal issues. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Completed and merged via PR #1 (2026-07-06).
Player Character | Jump | Create Input Action for Jump (Spacebar). Call Jump() and StopJumping() on the Character Movement Component. Tune MaxJumpHeight in CMC settings. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Completed and merged via PR #1 (2026-07-06).
Player Character | Interact (E / LMB) | Create Input Action for Interact (E key and Left Mouse Button). On trigger, perform a line trace from the camera. If hit actor implements interface_interact, call Interact(). | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Completed and merged via PR #2 (2026-07-13).
Player Character | Health / Defeat System | Add a CurrentHealth float variable (default 100). Create TakeDamage event that decrements health and checks for <= 0 to trigger the Lose condition. Expose via UI. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Implemented on BP_PlayerChar via Event AnyDamage. Defeat threshold corrected to Health <= 0.0 during testing. Merged via feature/death-restart.
Puzzle Systems | Timed Puzzle | Build a Blueprint actor with a countdown timer (UE Timer by Event). Player must complete a sequence of interact events before the timer expires. Failure resets the puzzle. | Unreal Engine 5 | Final | Final | Self | N | Minimum of one timed puzzle required per design doc; requirement is retained, not removed. Rescheduled to the Final phase for Milestone Two so the Alpha build concentrates on the environmental puzzle, health/defeat loop, HUD, and level blockout.
Puzzle Systems | Environmental Puzzle | Colored-button puzzle. Several colored buttons (BP_Button) are placed in the room with matching colored carryable objects (MAT_Color). Placing an object on the button of the same color presses that button down. Once all buttons are satisfied, the puzzle fires an event that opens BP_Door to the next area. | Unreal Engine 5 | Alpha | Alpha | Self | Y | Minimum of one environmental puzzle required per design doc. Implements the colored-button mechanic from the Module Four Skills Implementation Plan. Button merged via PR #5 (2026-07-20); door merged via PR #3 (2026-07-13).
Puzzle Systems | Interactable Objects | Create a Blueprint Interface (interface_interact) with an Interact function. All puzzle actors implement this interface. Player line trace calls the interface on valid hits. | Unreal Engine 5 | Alpha | Alpha | Self | Y | Completed and merged via PR #2 (2026-07-13). Implemented as interface_interact.
Puzzle Systems | Physics Grab / Carry / Drop | Player grabs a movable physics object via the interact line trace, carries it in front of the first-person camera (Physics Handle or attach-to-component), and drops it on input. Used to move weighted objects onto pressure plates and into sockets. | Unreal Engine 5 | Alpha | Alpha | Self | Y | Completed and merged via PR #2 (2026-07-13) as BP_PhysicsPlayer.
Puzzle Systems | Collectible / Key-Item System | Overlap + interact to collect energy cells / key shards. Each pickup destroys itself and increments a stored count (e.g., EnergyCellCount) shown on the HUD. Puzzle doors and gates check the count to allow progression. | Unreal Engine 5 | Alpha | Alpha | Self | Y | Completed and merged via PR #2 (2026-07-13) as BP_CollectiblePIckup. HUD counter display is outstanding.
Enemy | Turret Enemy | Blueprint turret (BP_Turrent) that detects the player within range, rotates to track them, and fires BP_TurrentProjectile on a Timer by Event. The projectile applies damage to the player on hit, providing the damage source for the health/defeat system. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | Completed and merged via PR #4 (2026-07-13).
Boss | Boss Actor | Create a Boss Blueprint with health variable, damage zones, and state machine (Idle, Attacking, Defeated). Boss must be defeatable only through environmental interaction. | Unreal Engine 5 | Alpha | Final | Self | N
Boss | Environment-Based Defeat Mechanic | Implement at least one trigger/mechanism in the boss arena that damages the boss when the player interacts with it (e.g., drop trap, throwable physics object, arena hazard). | Unreal Engine 5 | Alpha | Final | Self | N | Boss fight must utilize skills learned earlier in the level.
Game Manager | Win Condition | Create a Game Manager Blueprint (or use GameMode). When boss is defeated, fire Win event: stop game timer, show Win screen widget, disable player input. | Unreal Engine 5 | Alpha | Final | Self | N
Game Manager | Lose Condition | When player health reaches 0, fire Lose event: show Lose screen widget, offer Restart option. Wire Restart to OpenLevel(current level). | Unreal Engine 5 | Alpha | Alpha | Self | Y | Rescoped to Alpha for Milestone Two: defeat now prints a lose message and reloads the level via Open Level, replacing the previous Quit Game behaviour. The styled Lose screen widget remains in Final. Merged via feature/death-restart.
Game Manager | Mission Objective Display | Show the level objective to the player at the start point via a Widget Blueprint (UMG). Displayed as a brief on-screen prompt; dismissed by player input or after a set time. | Unreal Engine 5 | Alpha | Alpha | Self | N
UI / HUD | Player Health Display | Create a HUD Widget Blueprint with a health bar (Progress Bar bound to CurrentHealth / MaxHealth). Add widget to viewport on BeginPlay. | Unreal Engine 5 | Alpha | Alpha | Self | N | Required per design doc.
UI / HUD | Game Timer Display | Add a Game Timer float to Game Manager, incrementing each second via Timer by Event. Bind a Text block in the HUD widget to display elapsed time in MM:SS format. | Unreal Engine 5 | Alpha | Alpha | Self | N | Required per design doc.
UI / HUD | Interact Prompt (Contextual) | Contextual prompt widget appears when the interact line trace hits a valid interface_interact within range; hides when no valid target is found. | Unreal Engine 5 | Alpha | Final | Self | N | Listed in design doc UI section. Rescoped to Final for Milestone Two; not required for the Alpha build.
UI / HUD | Boss Health Bar | Boss health bar widget appears on entering the boss arena, bound to the boss health variable; hidden outside the encounter. | Unreal Engine 5 | Alpha | Final | Self | N | Listed in design doc UI section.
UI / HUD | Win / Lose Screens | Create separate Widget Blueprints for Win and Lose states. Win screen shows completion time. Lose screen shows a Restart button. Both disable gameplay input. | Unreal Engine 5 | Alpha | Final | Self | N
Level Design | Level Blockout | Block out the entire level using BSP or cube meshes. No asset packs or Starter Content. Layout must naturally guide the player without mechanical handholding. | Unreal Engine 5 | Pre-Alpha | Alpha | Self | Y | No asset packs or Starter Content per design doc. Level blocked out 2026-07-27 using the engine modeling tools within the existing map: outdoor surface approach, an enterable entrance building with a door and windows, and the puzzle area. All geometry is primitive-based with no imported assets.
Level Design | Puzzle Area 1 — Timed | Design and dress the timed puzzle room within the blocked-out level. Integrate timed puzzle Blueprint. Ensure room teaches the interact mechanic before requiring it under pressure. | Unreal Engine 5 | Alpha | Final | Self | N
Level Design | Puzzle Area 2 — Environmental | Design and dress the environmental puzzle room. Integrate pressure plate and physics object setup. Room must be completable without external instruction. | Unreal Engine 5 | Alpha | Final | Self | N
Level Design | Boss Arena | Design the boss arena with all environmental defeat mechanics placed and clearly readable. Arena layout must reinforce skills practiced in the two puzzle areas. | Unreal Engine 5 | Alpha | Final | Self | N
Repository | Feature Branching | Create a branch per feature (e.g., feature/player-movement, feature/timed-puzzle). Merge via pull request when feature is complete and tested. Tag PR with resolved issue. | GitHub / Git | Pre-Alpha | Final | Self | N | Required per design doc.
Repository | Commit Discipline | Label every commit with the feature it addresses (e.g., 'feat: add jump input action'). Commit after each logical unit of work — not just at milestones. | GitHub / Git | Pre-Alpha | Final | Self | N
Repository | Issue / Task Tracking | Create a GitHub Issue for each row in this traceability matrix. Resolve issue and reference it in the pull request when the feature branch is merged. | GitHub | Pre-Alpha | Final | Self | N
Code Quality | Blueprint Comments | Every Blueprint node group must have a Comment Box describing its purpose. Complex event graphs should have section headers. Required by design doc. | Unreal Engine 5 | Pre-Alpha | Final | Self | N | Design doc requires all code be commented.
Code Quality | No Tick Misuse | Audit all Blueprints before submission. Event Tick may only drive visual/cosmetic updates. All looping logic must use Timer by Event or Timer by Function Name. | Unreal Engine 5 | Alpha | Final | Self | N | Explicit requirement in design doc Code section.

## Test Plan
Test Plan
GitHub Repository Link: | https://github.com/kptmail-game/SNHU_GAM303_FPSPuzzle
Test Feature | Description of Test | Pass / Fail | Bugs | Runtime Errors | Updates / Error Resolution
First-Person Camera | Enter PIE. Verify camera is at eye level. Move mouse to confirm look rotates correctly in X and Y. Check no roll occurs.
WASD Movement | In PIE, press W/A/S/D and verify character moves in correct directions relative to camera facing. Check no input bleeds across axes.
Mouse Look | Move mouse in all directions; confirm pitch clamps at ~80° up/down. Verify yaw is unclamped. Check look speed feels natural.
Jump (Spacebar) | Press Spacebar in PIE. Confirm character leaves the ground and lands correctly. Verify jump cannot be triggered mid-air (no double-jump unless intended).
Interact — E / LMB | Place a test actor implementing interface_interact. Walk within range and press E and LMB separately. Confirm print string fires for both inputs. Confirm out-of-range does not fire.
Health / Defeat System | Take turret fire in PIE. Confirm Health decrements by the damage amount on each hit using the debug print. Continue taking damage until Health reaches zero and confirm the defeat branch fires. | Pass | Defeat did not fire when Health reached exactly zero. The player remained alive at zero health until a further hit pushed the value negative, so defeat always triggered one hit late. | None. No runtime errors or blueprint warnings were logged in the Output Log. | Root cause was a strict less-than comparison (Health < 0.0) on the defeat branch, which evaluates false at exactly zero. Changed to less-than-or-equal (Health <= 0.0) so defeat fires as soon as health is depleted. Retested against turret damage and defeat now triggers on the hit that brings health to zero.
Timed Puzzle | Trigger the timed puzzle. Confirm countdown timer appears and counts down correctly. Let timer expire — confirm failure/reset occurs. Complete puzzle before timer — confirm success fires. | Not Tested |  |  | Deferred to Final phase per the rescoped traceability matrix; feature is not implemented in the Alpha build.
Environmental Puzzle | Carry each colored object onto its matching colored button. Confirm a button only presses for an object of its own colour and ignores mismatched objects. Confirm the door opens once every button is satisfied. Remove an object and confirm that button releases and the door re-locks.
Interactable Objects (interface_interact) | Test all actors implementing interface_interact. Confirm line trace from camera hits each one within expected range. Confirm interface call does not error on any actor.
Boss Actor — States | Enter boss arena. Confirm boss starts in Idle. Approach to trigger attack state. Confirm attack animations/logic fire. Defeat boss — confirm Defeated state transitions correctly. | Not Tested |  |  | Deferred to Final phase per the rescoped traceability matrix; feature is not implemented in the Alpha build.
Boss — Environmental Defeat Mechanic | Use the environmental defeat mechanism (e.g., arena trigger) on the boss. Confirm boss health decrements. Repeat until boss health reaches 0. Confirm Win condition fires. | Not Tested |  |  | Deferred to Final phase per the rescoped traceability matrix; feature is not implemented in the Alpha build.
Win Condition | Defeat the boss and confirm: Win screen widget displays, game timer stops, player input is disabled, completion time is shown correctly. | Not Tested |  |  | Deferred to Final phase per the rescoped traceability matrix; feature is not implemented in the Alpha build.
Lose Condition | Reduce player health to zero using turret fire. Confirm the defeat message is displayed, then confirm the level reloads automatically and that health, collectibles, and door state are reset on the new run. | Pass | Defeat closed the application instead of restarting the level, ending the play session entirely. | None. No runtime errors or blueprint warnings were logged in the Output Log. | Root cause was a Quit Game node wired to the defeat branch. Replaced with a lose message, a 1.5 second delay, and an Open Level call targeting TestEnvironment. Reloading the map rebuilds the player character from its default values, so health, collectibles, and door state reset without any additional wiring. Retested and the level reloads cleanly. The styled Lose screen widget with a Restart button remains scheduled for the Final phase.
Mission Objective Display | Load the level. Confirm the objective widget appears at the start point. Verify text is readable and widget dismisses correctly (by input or timeout).
HUD — Health Bar | Confirm health bar is visible on HUD from game start. Take damage — confirm bar decrements in real time. Heal (if applicable) — confirm bar increments.
HUD — Game Timer | Confirm timer starts at 0:00 on level load and increments each second. Confirm timer stops on Win or Lose condition. Verify MM:SS format is correct past 9:59.
Level Flow / Blockout | Walk the level end to end without reading any documentation. Confirm the layout naturally guides the player from the outdoor approach, through the entrance building, and into the puzzle area using sightlines and framing rather than explicit waypoints. Boss arena routing is deferred to the Final phase.
No Asset Packs / Starter Content | Review Content Browser. Confirm no Starter Content folder, no Marketplace assets. All meshes and materials are custom or created within the project.
Blueprint Comments | Open every Blueprint created. Confirm each node group has a Comment Box. Confirm no large uncommented graph sections exist.
No Tick Misuse | Open all Blueprints. Search for Event Tick nodes. Confirm each Tick usage is cosmetic only. Confirm all looping game logic uses Timer by Event or Timer by Function Name.
Feature Branching (Git) | Review GitHub repo. Confirm a branch exists per major feature. Confirm each branch was merged via pull request. Confirm PRs reference resolved issues.
Commit Quality (Git) | Review commit history. Confirm commits are frequent (not just milestone-end dumps). Confirm commit messages describe the feature added (e.g., 'feat: implement pressure plate overlap logic').
Physics Grab / Carry / Drop | Grab a movable physics object via the interact line trace. Confirm it attaches in front of the camera and follows player movement. Drop it and confirm physics resume. Place it on a pressure plate and confirm the plate registers it.
Collectible / Key-Item System | Overlap a collectible and press interact. Confirm it is collected only on input (not on overlap alone), destroys itself, and increments the HUD counter. Verify a gated door/terminal checks the count correctly before allowing progression.
Interact Prompt (Contextual) | Look at a valid interface_interact within range and confirm the interact prompt widget appears. Look away or step out of range and confirm it hides. Confirm it never shows for non-interactable geometry. | Not Tested |  |  | Deferred to Final phase per the rescoped traceability matrix; feature is not implemented in the Alpha build.
Boss Health Bar | Enter the boss arena and confirm the boss health bar widget appears, bound to boss health. Damage the boss via an arena mechanism and confirm the bar decrements. Leave/win and confirm the bar hides. | Not Tested |  |  | Deferred to Final phase per the rescoped traceability matrix; feature is not implemented in the Alpha build.
Turret Enemy | Enter the turret's detection range. Confirm it rotates to track the player and begins firing on a fixed interval. Confirm projectiles travel, collide, and are destroyed on impact. Take a hit and confirm player health decrements. Leave range and confirm the turret stops firing.
Level Geometry Collision | Walk the blockout level end to end in PIE. Confirm the player is blocked by every wall, floor, and the exterior of the entrance building. Confirm the player can pass through each carved doorway and is still blocked by the surrounding wall. | Pass | (1) Player clipped through all geometry created with the engine modeling tools. (2) After collision was added, the carved doorways became impassable. | None. No runtime errors or blueprint warnings were logged in the Output Log for either issue. | (1) Meshes generated by the modeling tools are created with zero collision primitives, and setting a Collision Preset only defines the collision response, not the collision geometry. Resolved by adding simplified collision to the source static mesh assets. (2) Simplified box collision encloses the entire mesh and seals boolean-carved apertures. Resolved by removing the simplified collision and setting Collision Complexity to Use Complex Collision As Simple on the affected wall assets, so the render geometry is used for collision and the openings remain passable. Both fixes were made on the source assets, so every copy-pasted instance inherited them. Retested and passed.